## Sheet1
COMMUNITY REPAIR EVENT PROJECT PLANNING
Input event date here and all dates below will populate.
|  |  |  | INPUT CRE DATE: | 2019-08-03
Days
| Out |  | Task | who | Notes
2019-04-25 | 100 |  | Review resources on how to start a project |  | see online: Culture of Repair, Fixit Clinic, Restart Proj, Repair Café
2019-05-05 | 90 |  | Begin to develop volunteer pool |  | fixers. If café: café organizers as well
2019-05-05 | 90 |  | Identify candidate collaborators
2019-05-05 | 90 |  | Identify candidate venues and dates available
2019-05-05 | 90 |  | Identify candidate dates |  | 3- hour window + 2 hours set up, 1 hour break down
2019-05-05 | 90 |  | Confirm date with venue
2019-05-05 | 90 |  | Confirm date with collaborators
2019-05-15 | 80 |  | Contact potential sponsors
2019-05-15 | 80 |  | Contact potential donors
2019-05-15 | 80 |  | Identify publicity channelts |  | soc media, local news, local allied orgs, sponsors, donors
2019-05-15 | 80 |  | Identify publicity allies |  | who will like / boost / retweet / etc.
2019-05-15 | 80 |  | Prepare publicity content: images and text |  | press releases, soc media, fliers, newsletters, for all parties
2019-05-25 | 70 |  | Post to public calendars |  | organizer, collaborators, sponsor, venue
2019-05-25 | 70 |  | Request include in newsletters |  | organizer, collaborators, sponsor, venue
2019-05-30 | 65 |  | Review supplies on hand |  | see below
2019-05-30 | 65 |  | Procure missing supplies |  | solicitation or purchase: local hardware store
2019-06-19 | 45 |  | Notify volunteers of date
2019-06-19 | 45 |  | Post to social media: pin to profile |  | organizer, collaborators, sponsor, venue
2019-06-19 | 45 |  | Submit to publicity channels requiring lead time |  | e.g., community newspapers and radio stations
2019-06-18 | 46 |  | Begin develop host volunteer pool |  | registration etc.; if café, support vols
2019-07-04 | 30 |  | Notify/remind donors and sponsors of event
2019-07-11 | 23 |  | Email volunteers asking for commitment to date
2019-07-19 | 15 |  | Create and make copies of waivers
2019-07-19 | 15 |  | Remind local hardware store of event
2019-07-19 | 15 |  | email vol pool asking fixers commit
2019-07-24 | 10 |  | Post soc media: organizers, venue, sponsors, donors, vols |  | Twitter, Facebook, Mastodon, Linked In, Tumbler, Instagram, NextDoor
2019-07-24 | 10 |  | Request allies support |  | Direct message or email with link to post
2019-07-24 | 9 |  | Email volunteers signed up with info abt event
2019-07-24 | 10 |  | Confirm have supplies on hand
2019-07-25 | 9 |  | Contact local news outlets to be featured event
2019-07-27 | 7 |  | Arrange pizza and drinks for vols |  | include vegetarian and vegan
2019-07-29 | 5 |  | Email volunteers signed up with info abt event
2019-07-30 | 4 |  | Remind local hardware store of event
2019-07-30 | 4 |  | Post soc media: organizers, venue, sponsors, donors, vols |  | Twitter, Facebook, Mastodon, Linked In, Tumbler, Instagram, NextDoor
2019-07-30 | 4 |  | Request allies support |  | Direct message with link to post
2019-07-30 | 4 |  | Registration Volunteers |  | Confirm have 2-3 vols & they understand process & data capture
2019-07-31 | 3 |  | Arrange for 3 - 4 computers for registration, if using |  | must be user-friendly
2019-07-31 | 3 |  | Confirm have registration materials are on hand |  | see below
2019-08-02 | 1 |  | Email volunteers last minute info and reminder
2019-08-03 | 0 |  | FIX! |  | Have fun and learn and celebrate repair!
2019-08-04 | -1 |  | Thank volunteers
2019-08-04 | -1 |  | Thank sponsors and donors
2019-08-06 | -3 |  | Post images soc media: org, venue, sponsors, donors
2019-08-06 | -3 |  | Request allies like and support |  | Direct message with link to post
DETAILS ABOUT TASKS
Prepare images and text for different formats:
Twitter, Facebook, Mastodon, Linked In
Tumbler, Instagram, NextDoor
Local news organizations, paper, online, radio
Newsletters of various organizations
SUPPLIES
fixers bring tools, basic supplies should have on hand
|  |  | prepare comprehensive list |  | see online resources: Fixit Clinic, Restart Proj, Cul Rep Proj, Repair Café
identify what need
REGISTRATION TABLE SUPPLIES
|  |  | BELL!! |  | VERY IMPORTANT, EASY TO OVERLOOK
|  | · Scale | Pens, nametags, Contribution Jar, Camera, Bell
sign FIXED!
waivers
|  |  | registration pages |  | at least for data collection: outcome of repair attempt
|  |  | donor recognition |  | material to post
|  |  | 3-4 computers |  | user friendly volunteers key registration for participants